## CI Project Tracker
Project # | Project Title | Department | Project Leader | Start Date | Define Target Date | Define Actual Date | Measure Target Date | Measure Actual Date | Analyse Target Date | Analyse Actual Date | Improve Target Date | Improve Actual Date | Control Target Date | Control Actual Date | Current Phase | Days Overdue | Status | Comment
Project 01 | Lead Time Reduction | Production | Tom | 2026-01-01 | 2026-01-31 | 2026-01-31 | 2026-04-01 | 2026-04-01 | 2026-05-31 | 2026-06-02 | 2026-07-30 | 2026-07-30 | 2026-09-28 | 2026-10-01 | Completed |  | Completed
Project 02
Project 03
Project 04
Project 05
Project 06
Project 07
Our standard schedule is: Start → Define 30 → Measure 90 → Analyze 150 → Improve 210 → Control 270 days
Formulas:
Define Target Date = [Start Date]+30
Measure Target Date = [Start Date]+90
Analyse Target Date = [Start Date]+150
Improve Target Date = [Start Date]+210
Control Target Date = [Start Date]+270
Days Overdue = IF([Start Date]="","",IF([Current Phase]="Completed","",IF(TODAY()>SWITCH([Current Phase],"Define",[Define Target Date],"Measure",[Measure Target Date],"Analyze",[Analyse Target Date],"Improve",[Improve Target Date],"Control",[Control Target Date]),TODAY()-SWITCH([Current Phase],"Define",[Define Target Date],"Measure",[Measure Target Date],"Analyze",[Analyse Target Date],"Improve",[Improve Target Date],"Control",[Control Target Date]),"")))

## Project 01
Define Phase | Project # | Project 01 | Project Title | Reduce Manufacturing Lead Time
| Leader | Richard | Team Member | Tom, Joe, Mary
| Problem Statement | Lead time is too long, adversly affecting on time delivery and customer satisfaction.
| KPI | Manufacturing lead time
| Baseline | 15 days | Target | 5 days
| Exptected Benefit $ | $100k/year
Measure Phase | Data Collection Plan
Baseline Validation
Supporting Evidence
Analyze Phase | Potential Causes
Verified Root Causes
Supporting Evidence
Improve Phase | Improvement Actions
Validation Results
Supporting Evidence
Control Phase | Control Plan
Sustained Results
Supporting Evidence
Actual Result | 8 days |  | Verified Business Benefit $ | $115k/year
Approved by Champion |  |  | Date Completed